## Instructions
Lab 2 - Field-Level Action Register
Participant workbook ¦ Compare meeting notes with the current register and change only approved fields.
Core control rule
For an existing Action ID, update only the field explicitly changed in the meeting. Preserve every other value exactly as it appears in the Action Register.
Step | Action | Output | Control | Time | Source | Where to record | Complete when
1 | Inspect both supplied sources | Confirmed meeting and workbook | Use the master Excel values as current state | 5 min | Meeting Notes + Action Register | No entry yet | You can name both sources
2 | Extract candidate changes in Copilot Chat | Field-level proposed delta | One row per changed field | 7 min | Meeting Notes | Field Change Queue | No full-row update is proposed
3 | Compare every proposal with Excel | Current and proposed values | The current value must match the workbook | 8 min | Action Register | Field Change Queue | Matches use Action IDs
4 | Review exceptions | Approved, Rejected or Hold | Do not guess missing or conflicting values | 5 min | Both sources | Both review queues | Every candidate has a decision
5 | Apply approved changes | Updated Action Register | Only named fields may change | 7 min | Approved queues | Action Register | No unapproved cell changed
6 | Audit before and after | Changed-cell evidence | Every edit maps to an approved Change ID | 5 min | Snapshot + current | Before-After Audit | Validation shows PASS
Workbook colour guide
Yellow cells | Participant input | Blue sections | Reference or formula-controlled
Green result | Approved or passed | Red result | Exception requiring review

## Action Register
Project Atlas - Action Register
Master action data ¦ Participant edits belong only in approved fields and approved new rows.
Current state before the 8 September meeting. Rows 13-40 are reserved for approved additions.
Action ID | Project | Action | Owner | Due Date | Priority | Status | Dependency | Source Meeting | Last Updated | Notes | Duplicate Check | Required Fields
ACT-014 | Project Atlas | Complete SSO timeout retest | Priya Nair | 2026-09-10 | High | In Progress | Security test environment | Security Readiness - 03 Sep 2026 | 2026-09-03 | External access disabled until the test passes | OK | OK
ACT-015 | Project Atlas | Confirm UAT environment delivery | Mark Chen | 2026-09-08 | High | In Progress | Network configuration | Technical Sync - 02 Sep 2026 | 2026-09-02 | Environment expected Tuesday morning | OK | OK
ACT-016 | Project Atlas | Validate migrated user accounts sample | Mark Chen | 2026-09-11 | High | Not Started | Data extract version 3 | Migration Workshop - 01 Sep 2026 | 2026-09-01 | Validate a sample of 50 user accounts | OK | OK
ACT-017 | Project Atlas | Draft UAT participant communication | Sofia Rossi | 2026-09-12 | Medium | In Progress | Confirmed UAT start | Change Readiness - 03 Sep 2026 | 2026-09-03 | Draft includes participation instructions | OK | OK
ACT-018 | Project Atlas | Publish UAT access guide | Daniel Brooks | 2026-09-09 | Medium | Not Started | Environment access | Service Desk Planning - 29 Aug 2026 | 2026-08-29 | Include password-reset guidance | OK | OK
ACT-019 | Project Atlas | Confirm Service Desk escalation rota | Daniel Brooks | 2026-09-13 | Medium | In Progress | Support manager availability | Service Readiness - 04 Sep 2026 | 2026-09-04 | Weekend rota pending | OK | OK
ACT-020 | Project Atlas | Review portal homepage wording | Sofia Rossi | 2026-09-20 | Low | Backlog | Brand review | Design Review - 28 Aug 2026 | 2026-08-28 | Post-UAT improvement | OK | OK
ACT-021 | Project Atlas | Obtain UAT go/no-go approval | Hanna Serednytska | 2026-09-14 | High | Not Started | Security and environment evidence | Steering Committee - 04 Sep 2026 | 2026-09-04 | Approval required before launch | OK | OK

## Field Change Queue
Field Change Queue
One row per proposed field change for an existing Action ID. Never replace the whole row.
Yellow cells are participant input. Compare the exact current Excel value before approving a proposed value.
Change ID | Action ID | Classification | Field to Change | Current Value | Proposed Value | Exact Meeting Evidence | Missing or Conflict | Human Decision | Applied?

## New Action Queue
New Action Queue
Create a full row only when the task and all required values are sufficiently confirmed.
A missing or conflicting required field means Hold. Do not invent values to make a new action complete.
Candidate ID | Action Description | Owner | Due Date | Priority | Status | Dependency | Source Meeting | Exact Evidence | Missing or Conflict | Human Decision | Assigned Action ID | Applied?

## Before Snapshot
Before Snapshot
Read-only comparison copy of the original register before any Lab 2 changes.
Do not edit this sheet. Use it to prove that unchanged fields remained identical.
Action ID | Project | Action | Owner | Due Date | Priority | Status | Dependency | Source Meeting | Last Updated | Notes
ACT-014 | Project Atlas | Complete SSO timeout retest | Priya Nair | 2026-09-10 | High | In Progress | Security test environment | Security Readiness - 03 Sep 2026 | 2026-09-03 | External access disabled until the test passes
ACT-015 | Project Atlas | Confirm UAT environment delivery | Mark Chen | 2026-09-08 | High | In Progress | Network configuration | Technical Sync - 02 Sep 2026 | 2026-09-02 | Environment expected Tuesday morning
ACT-016 | Project Atlas | Validate migrated user accounts sample | Mark Chen | 2026-09-11 | High | Not Started | Data extract version 3 | Migration Workshop - 01 Sep 2026 | 2026-09-01 | Validate a sample of 50 user accounts
ACT-017 | Project Atlas | Draft UAT participant communication | Sofia Rossi | 2026-09-12 | Medium | In Progress | Confirmed UAT start | Change Readiness - 03 Sep 2026 | 2026-09-03 | Draft includes participation instructions
ACT-018 | Project Atlas | Publish UAT access guide | Daniel Brooks | 2026-09-09 | Medium | Not Started | Environment access | Service Desk Planning - 29 Aug 2026 | 2026-08-29 | Include password-reset guidance
ACT-019 | Project Atlas | Confirm Service Desk escalation rota | Daniel Brooks | 2026-09-13 | Medium | In Progress | Support manager availability | Service Readiness - 04 Sep 2026 | 2026-09-04 | Weekend rota pending
ACT-020 | Project Atlas | Review portal homepage wording | Sofia Rossi | 2026-09-20 | Low | Backlog | Brand review | Design Review - 28 Aug 2026 | 2026-08-28 | Post-UAT improvement
ACT-021 | Project Atlas | Obtain UAT go/no-go approval | Hanna Serednytska | 2026-09-14 | High | Not Started | Security and environment evidence | Steering Committee - 04 Sep 2026 | 2026-09-04 | Approval required before launch

## Before-After Audit
Before-After Audit
Record every changed cell and map it to an approved Change ID or approved new-action candidate.
The final audit fails if a changed cell has no approved queue entry or if an approved change was not applied.
Changed Cell | Action ID | Field | Before Value | After Value | Approved Change ID | Matching Review Entry? | Audit Result

## Validation
Validation
Formula-driven checks for the completed action register and review queues.
Check | Result | Final human checks
Current action count | 8 | Check | Expected | Participant confirmation
Original action count | 8 | Every changed cell has an approved ID | Yes
Approved field changes | 0 | Every approved field change was applied | Yes
Approved new actions | 0 | Unchanged fields stayed identical | Yes
Expected action count | 8 | Held values stayed unchanged | Yes
Duplicate ID warnings | 0 | No suggestion became an action | Yes
Missing required-field warnings | 0
Action-count reconciliation | PASS
Expected workshop result after the correct changes: 10 actions, 5 approved field changes, 2 approved new actions, 0 duplicate IDs and 0 missing required fields.