MEETING NOTES

Project Atlas - UAT Readiness

Source document for Lab 2: field-level action-register updates

| DATE | 8 September 2026 | TIME | 10:00-10:35 |
| --- | --- | --- | --- |
| CHAIR | Hanna Serednytska | LOCATION | Microsoft Teams |

# Meeting objective

Confirm the remaining work required to begin user acceptance testing and record only changes that were explicitly agreed during the meeting.

CHAIR'S CONTROL RULE When an existing action changes, update only the field that was explicitly changed. Preserve every other value already recorded in the master Excel register.

# Participants

Hanna Serednytska - Project Manager and meeting chair

Priya Nair - Security Lead

Mark Chen - Technical Lead

Sofia Rossi - Business Readiness Lead

Daniel Brooks - IT Service Manager

# Agenda

| Time | Topic | Required outcome |
| --- | --- | --- |
| 5 min | Opening and readiness criteria | Confirm what must change today |
| 8 min | Security and environment | Confirm dates and restrictions |
| 8 min | Data and communications | Confirm ownership and completion |
| 7 min | Service readiness | Confirm operational actions |
| 7 min | Readback | Separate approved changes from unresolved items |

# Discussion notes

## 1. Security and environment

Priya confirmed: "The SSO timeout retest will take place on Friday, 11 September at 15:00, not Thursday, 10 September. I remain responsible for completing the test."

Mark confirmed: "The UAT environment delivery is now Wednesday, 9 September rather than Tuesday, 8 September. The network configuration remains the dependency."

The group retained the existing restriction that external access must remain disabled until the SSO timeout test passes.

## 2. Data validation and participant communication

Hanna confirmed: "Sofia will take ownership of validating the migrated-user sample from Mark. The current deadline of 11 September remains unchanged."

Sofia reported: "The UAT participant communication draft is complete." No change to its owner, deadline or priority was discussed.

## 3. Service readiness

Daniel confirmed that the UAT access guide remains due on 9 September. No other change was requested for that action.

Daniel stated: "The Service Desk escalation rota must be ready by Saturday, 12 September instead of Sunday, 13 September. I remain the owner."

## 4. Go/no-go timing - unresolved

Hanna proposed moving the UAT go/no-go approval to Friday, 11 September. Daniel said the official target should remain Monday, 14 September until sponsor availability is confirmed. The team did not agree a new date.

UNRESOLVED The go/no-go deadline contains conflicting statements. The existing Excel value must remain unchanged until the sponsor confirms the date.

## 5. New work discussed

Priya agreed to document the external-access restriction for the UAT participants by 11 September. Hanna confirmed that this is a high-priority action. It depends on the SSO timeout test.

Mark agreed to upload the UAT test credentials to the approved secure location by 9 September at 12:00. Hanna confirmed that this is high priority and depends on delivery of the UAT environment.

Sofia agreed to distribute the training materials, but the team did not confirm a deadline or priority. The item remains open for clarification.

The group discussed bringing the portal homepage redesign forward from the post-UAT backlog. No owner accepted the work, no deadline was agreed and the chair did not record a new commitment.

# Closing readback

| Readback item | Meeting outcome |
| --- | --- |
| Existing actions | Change only the explicitly agreed field; preserve all other values. |
| New actions | Create a complete row only when the task and required values are sufficiently confirmed. |
| Conflicts | Hold the proposed change and retain the current Excel value. |
| Suggestions | Do not turn general discussion into an action. |

# Source and handling note

This is a synthetic workshop case. It contains no customer, employee or production information. Participants should use only the supplied case files during the exercise.