## Import Instructions
Project Aurora - SharePoint Import Pack
Synthetic workshop data ¦ Use the ProjectRegisterTable to create the SharePoint list IT Project Delivery Register.
Step | Instruction | Controlled test
1 | Save this workbook in an approved workshop location. | After the dashboard is created, change only IT-017 RAG Status from Amber to Red. Total projects, budgets, schedule values and all other fields must remain unchanged.
2 | Open the target SharePoint site and select New > List.
3 | Select From Excel and upload this workbook.
4 | Select ProjectRegisterTable when SharePoint asks which table to import.
5 | Name the list IT Project Delivery Register.
6 | Review the detected column types before creating the list.
7 | Keep Project ID and names as text; budgets and counts as numbers; dates as date and time columns.
8 | Do not correct the deliberate data-quality issues during import.
9 | Use the separate validation workbook to verify dashboard totals and the one-field test.

## Project Register
Project ID | Project Name | Department | Project Manager | Sponsor | Stage | RAG Status | Approved Budget | Forecast Cost | Budget Variance | Planned Go-Live | Forecast Go-Live | Schedule Variance Days | Open High Risks | Open Critical Issues | Benefits Status | Last Update Date | Decision Required | Decision Owner | Evidence Status | Data Classification
IT-001 | Identity and Access Modernisation | Infrastructure | PM-01 | SP-01 | Build | Amber | 420000 | 438000 | 18000 | 2026-10-15 | 2026-10-29 | 14 | 3 | 0 | On track | 2026-08-25 | Yes | SP-01 | Confirmed | Synthetic training data
IT-002 | Customer Service Knowledge Hub | Customer Operations | PM-02 | SP-02 | UAT | Green | 180000 | 176000 | -4000 | 2026-09-20 | 2026-09-20 | 0 | 1 | 0 | Tracking | 2026-08-27 | No |  | Confirmed | Synthetic training data
IT-003 | Data Retention Compliance | Security | PM-03 | SP-03 | Build | Amber | 140000 | 150000 | 5000 | 2026-11-01 | 2026-11-12 | 11 | 2 | 1 | At risk | 2026-08-24 | Yes | SP-03 | Partial | Synthetic training data
IT-004 | Network Segmentation Phase 2 | Infrastructure | PM-04 | SP-01 | Planning | Green | 310000 | 305000 | -5000 | 2026-12-10 | 2026-12-10 | 0 | 1 | 0 | Not started | 2026-08-26 | No |  | Confirmed | Synthetic training data
IT-005 | Finance Reporting Automation | Finance | PM-05 | SP-04 | UAT | Amber | 225000 | 239000 | 14000 | 2026-09-30 | 2026-10-10 | 10 | 2 | 0 | Tracking | 2026-08-23 | Yes | SP-04 | Confirmed | Synthetic training data
IT-006 | Legacy VPN Retirement | Security | PM-03 | SP-03 | Build | Red | 160000 | 198000 | 38000 | 2026-09-15 | 2026-11-01 | 47 | 5 | 2 | At risk | 2026-08-26 | No |  | Partial | Synthetic training data
IT-007 | Supplier Onboarding Portal | Procurement | PM-06 | SP-05 | UAT | Amber | 240000 | 252000 | 12000 | 2026-09-15 | 2026-09-29 | 14 | 4 | 1 | Tracking | 2026-08-27 | Yes | SP-05 | Confirmed | Synthetic training data
IT-008 | Cloud Cost Optimisation | Cloud Platform | PM-07 | SP-01 | Live | Green | 95000 | 88000 | -7000 | 2026-07-31 | 2026-07-28 | -3 | 0 | 0 | Realising | 2026-08-22 | No |  | Confirmed | Synthetic training data
IT-009 | Enterprise Search Upgrade | Digital Workplace |  | SP-02 | Planning | Amber | 275000 | 275000 | 0 | 2027-01-15 | 2027-01-29 | 14 | 2 | 0 | Not started | 2026-08-21 | Yes | SP-02 | Partial | Synthetic training data
IT-010 | Endpoint Management Renewal | Infrastructure | PM-08 | SP-01 | Live | Green | 130000 | 129000 | -1000 | 2026-08-20 | 2026-08-20 | 0 | 0 | 0 | Realising | 2026-08-26 | No |  | Confirmed | Synthetic training data
IT-011 | HR Case Management | People Operations | PM-09 | SP-06 | Build | Green | 210000 | 208000 | -2000 | 2026-11-20 | 2026-11-20 | 0 | 1 | 0 | Tracking | 2026-08-20 | No |  | Confirmed | Synthetic training data
IT-012 | Security Operations Analytics | Security | PM-03 | SP-03 | Planning | Amber | 360000 | 382000 | 22000 | 2027-02-15 | 2027-02-28 | 13 | 3 | 0 | Not started | 2026-08-25 | Yes |  | Partial | Synthetic training data
IT-013 | Contract Lifecycle Management | Legal | PM-10 | SP-07 | Discovery | Green | 120000 | 120000 | 0 | 2027-03-30 | 2027-03-30 | 0 | 1 | 0 | Not started | 2026-08-19 | No |  | Confirmed | Synthetic training data
IT-014 | Warehouse Mobility | Operations | PM-11 | SP-02 | UAT | Red | 500000 | 548000 | 48000 | 2026-09-10 | 2026-10-20 | 40 | 6 | 3 | At risk | 2026-08-27 | Yes | SP-02 | Confirmed | Synthetic training data
IT-015 | ESG Data Collection | Sustainability | PM-05 | SP-06 | Build | Green | 190000 | 194000 | 4000 | 2026-10-01 | 2026-11-15 | 45 | 2 | 0 | Tracking | 2026-08-24 | No |  | Partial | Synthetic training data
IT-016 | Mobile Device Refresh | Digital Workplace | PM-08 | SP-01 | Build | Green | 280000 | 274000 | -6000 | 2026-10-31 | 2026-10-31 | 0 | 1 | 0 | On track | 2026-08-27 | No |  | Confirmed | Synthetic training data
IT-017 | IT Service Catalogue | Service Management | PM-06 | SP-02 | UAT | Amber | 175000 | 181000 | 6000 | 2026-09-25 | 2026-10-02 | 7 | 2 | 1 | Tracking | 2026-08-26 | Yes | SP-02 | Confirmed | Synthetic training data
IT-018 | Archive Platform Migration | Infrastructure | PM-04 | SP-01 | Planning | Amber | 260000 | -5000 | -265000 | 2027-01-30 | 2027-02-15 | 16 | 2 | 0 | Not started | 2026-08-18 | Yes | SP-01 | Missing | Synthetic training data
IT-019 | Sales CRM Integration | Sales | PM-07 | SP-07 | Build | Green | 330000 | 328000 | -2000 | 2026-12-01 | 2026-12-01 | 0 | 1 | 0 | Tracking | 2026-08-25 | No |  | Confirmed | Synthetic training data
IT-020 | Privileged Access Management | Security | PM-03 | SP-03 | UAT | Red | 450000 | 489000 | 39000 | 2026-09-05 | 2026-10-15 | 40 | 7 | 2 | At risk | 2026-08-27 | Yes | SP-03 | Confirmed | Synthetic training data
IT-021 | Field Service Scheduling | Operations | PM-11 | SP-02 | Build | Amber | 205000 | 218000 | 13000 | 2026-10-20 | 2026-11-05 | 16 | 3 | 0 | Tracking | 2026-07-25 | Yes | SP-02 | Partial | Synthetic training data
IT-022 | Digital Expense Claims | Finance | PM-05 | SP-04 | Live | Green | 150000 | 147000 | -3000 | 2026-08-15 | 2026-08-12 | -3 | 0 | 0 | Realising | 2026-08-26 | No |  | Confirmed | Synthetic training data
IT-023 | Customer Identity Consolidation | Customer Operations | PM-02 | SP-02 | Build | Amber | 390000 | 405000 | 15000 | 2026-12-15 | 2027-01-10 | 26 | 4 | 1 | At risk | 2026-08-22 | Yes | SP-02 | Confirmed | Synthetic training data
IT-024 | Employee Access Portal | Digital Workplace | PM-09 | SP-06 | UAT | Green | 165000 | 162000 | -3000 | 2026-09-18 | 2026-09-18 | 0 | 1 | 0 | Tracking | 2026-08-27 | No |  | Confirmed | Synthetic training data
IT-025 | Employee Access Portal Phase 2 | Digital Workplace | PM-09 | SP-06 | Discovery | Green | 90000 | 90000 | 0 | 2027-04-15 | 2027-04-15 | 0 | 0 | 0 | Not started | 2026-08-20 | No |  | Partial | Synthetic training data
IT-026 | Procurement Spend Analytics | Procurement | PM-06 | SP-05 | Build | Amber | 200000 | 219000 | 19000 | 2026-11-10 | 2026-11-24 | 14 | 2 | 0 | Tracking | 2026-08-23 | Yes | SP-05 | Confirmed | Synthetic training data
IT-027 | Disaster Recovery Testing | Infrastructure | PM-04 | SP-01 | Planning | Amber | 110000 | 116000 | 6000 | 2026-10-30 |  | 0 | 2 | 0 | Not started | 2026-08-26 | Yes | SP-01 | Missing | Synthetic training data
IT-028 | Marketing Consent Management | Marketing | PM-10 | SP-07 | Build | Green | 185000 | 183000 | -2000 | 2026-11-15 | 2026-11-15 | 0 | 1 | 0 | Tracking | 2026-08-25 | No |  | Confirmed | Synthetic training data
IT-029 | API Management Upgrade | Cloud Platform | PM-07 | SP-01 | UAT | Amber | 300000 | 321000 | 8000 | 2026-09-28 | 2026-10-12 | 14 | 3 | 1 | At risk | 2026-08-27 | Yes | SP-01 | Partial | Synthetic training data
IT-030 | Records Classification | Legal | PM-10 | SP-07 | Discovery |  | 80000 | 82000 | 2000 | 2027-05-01 | 2027-05-01 | 0 | 1 | 0 | Not started | 2026-08-10 | No |  | Missing | Synthetic training data

## Field Definitions
Field Definitions
Recommended SharePoint types and dashboard use. Confirm types before list creation.
Field | Recommended SharePoint type | Required | Dashboard use | Control
Project ID | Single line of text | Yes | Search and record link | Do not invent missing values
Project Name | Single line of text | Yes | Filter, detail or exception table | Do not invent missing values
Department | Single line of text | Yes | Filter, detail or exception table | Do not invent missing values
Project Manager | Single line of text | Review | Filter, detail or exception table | Do not invent missing values
Sponsor | Single line of text | Review | Filter, detail or exception table | Do not invent missing values
Stage | Choice | Yes | Filter, detail or exception table | Do not invent missing values
RAG Status | Choice | Review | KPI, filter and chart | Never infer from dates
Approved Budget | Currency or number | Yes | Financial KPI and chart | Do not invent missing values
Forecast Cost | Currency or number | Yes | Financial KPI and chart | Do not invent missing values
Budget Variance | Currency or number | Review | Financial KPI and chart | Compare with Forecast Cost - Approved Budget
Planned Go-Live | Date and time (date only) | Review | Schedule and freshness | Do not invent missing values
Forecast Go-Live | Date and time (date only) | Review | Schedule and freshness | Do not invent missing values
Schedule Variance Days | Number | Review | Filter, detail or exception table | Do not invent missing values
Open High Risks | Number | Review | Filter, detail or exception table | Do not invent missing values
Open Critical Issues | Number | Review | Filter, detail or exception table | Do not invent missing values
Benefits Status | Choice | Review | Filter, detail or exception table | Do not invent missing values
Last Update Date | Date and time (date only) | Yes | Schedule and freshness | Do not invent missing values
Decision Required | Choice | Review | Filter, detail or exception table | Do not invent missing values
Decision Owner | Single line of text | Review | Filter, detail or exception table | Required only when Decision Required = Yes
Evidence Status | Choice | Review | Filter, detail or exception table | Do not invent missing values
Data Classification | Single line of text | Review | Filter, detail or exception table | Do not invent missing values