LAB 6 SOURCE FILE

Project Northstar - Readiness Review Notes

Meeting evidence containing facts, proposals, actions and unresolved items

| MEETING 25 August 2026 | DURATION 45 minutes | STATUS Draft notes - not an approval record |
| --- | --- | --- |

EVIDENCE BOUNDARY A comment in meeting notes is not automatically a confirmed decision. Preserve the speaker, status and uncertainty.

# Participants

Hanna Reed - Programme Manager (chair)

Priya Shah - Security Lead

Mark Jensen - Technical Lead

Sofia Lind - Operations Readiness Lead

Daniel Weber - Vendor Delivery Lead

Elena Novak - Business Owner

# Discussion record

## Security readiness

Priya confirmed that the penetration retest is booked for 10 September. External supplier access is not approved before the retest. She proposed allowing internal UAT and disabling external access until approval.

## UAT status

Mark reported 184 of 200 planned tests complete. Four Severity 1 defects remain open. Daniel expects fixes by 8 September, but this date is a vendor forecast, not a confirmed closure date.

## Migration

The readiness tracker shows 215 of 250 supplier records validated. Elena said Procurement can complete the remainder before launch. No accountable owner was confirmed for final sign-off.

## Training

Sofia reported 36 of 50 pilot users trained. She stated that Operations supports a conditional launch only if at least 90% complete training and the support owner is named.

## Launch date

Daniel suggested 29 September because the original 15 September date leaves no contingency after the security retest. The meeting did not approve this date.

## Cost of delay

Daniel stated that each week of delay could cost EUR 35,000. Finance was not present and no calculation was supplied.

## Proposed outcome

Hanna summarised a possible Conditional Go: revise the date, keep external access disabled until security approval, close all Severity 1 defects, reach the training threshold and confirm the migration sign-off owner. The Steering Committee has not approved this proposal.

# Actions recorded

| Action | Owner | Due | Status |
| --- | --- | --- | --- |
| Complete penetration retest | Priya Shah | 10 Sep 2026 | Confirmed |
| Provide fixes for four Severity 1 defects | Daniel Weber | 8 Sep 2026 | Forecast |
| Complete remaining user training | Sofia Lind | Before launch | Confirmed action; date incomplete |
| Confirm migration sign-off owner | Not confirmed | Not confirmed | Open |
| Prepare launch-date change request | Hanna Reed | 27 Aug 2026 | Confirmed |

# Unresolved items

Security approval remains conditional on the retest.

Four Severity 1 defects remain open.

Migration sign-off owner is not confirmed.

The EUR 35,000 weekly delay figure is unsupported.

The suggested 29 September date requires an approved change notice.

Conditional Go is a proposal, not an approved decision.

# How to interpret these notes

| Label | Meaning in the presentation |
| --- | --- |
| Confirmed fact | May be used when the statement is supported by a current authoritative source. |
| Forecast | Keep the forecast owner and label; do not present it as completed work. |
| Proposal | Show the decision still required and do not convert it into approval. |
| Not confirmed | Keep the missing owner, deadline, value or evidence visible. |

PARTICIPANT TASK Find at least one fact, one forecast, one proposal and one unsupported statement before creating the presentation.