LAB 6 SOURCE FILE

Project Northstar - Project Brief

Supplier Onboarding Platform | Steering Committee evidence pack

| VERSION 1.0 | ISSUED 20 August 2026 | STATUS Approved baseline |
| --- | --- | --- |

SOURCE RULE Treat this document as the approved baseline for scope, objectives and original launch date. Later approved change notices override only the fields they explicitly name.

# 1. Business context

Northstar Group is introducing a supplier-onboarding platform for Procurement and Operations. The pilot will cover 250 active and prospective suppliers and 50 internal users. SAP remains the system of record for activated suppliers.

# 2. Pilot objective and success targets

Reduce the average supplier-onboarding cycle from 12 to 7 business days within three months of launch.

Reduce manual follow-up emails by 30% within three months of launch.

Preserve independent banking-data verification and audit evidence.

Provide Procurement with one visible onboarding status per supplier.

IMPORTANT DISTINCTION The cycle-time and follow-up figures are targets. They are not benefits already achieved.

# 3. Approved scope

| In scope | Out of scope |
| --- | --- |
| Supplier intake and document collection | Automated supplier activation in SAP |
| Compliance-screening workflow and evidence | Global rollout beyond the pilot |
| Bank-detail verification hand-off | Changes to payment approval policy |
| Status tracking and internal notifications | Automatic resolution of compliance exceptions |

# 4. Baseline plan and funding

| Original pilot date | 15 September 2026 |
| --- | --- |
| Approved budget | EUR 240,000 |
| Programme sponsor | Lena Ortiz, Chief Operations Officer |
| Business owner | Elena Novak, Head of Procurement |
| Pilot groups | Procurement and Operations |
| Decision forum | Northstar Steering Committee |

# 5. Release-gate conditions

| Gate | Minimum condition |
| --- | --- |
| UAT | No open Severity 1 defects; accepted workaround for any open Severity 2 defect. |
| Security | Penetration retest passed or external access remains disabled under an approved restriction. |
| Data migration | All pilot supplier records validated before activation. |
| Training | At least 90% of the 50 pilot users complete training. |
| Operations | Support owner and first-week triage process confirmed. |

# 6. Decisions required from the Steering Committee

Confirm whether the pilot should proceed, proceed conditionally or be delayed.

Confirm whether external supplier access may remain disabled until security approval is complete.

Confirm the accountable owner for final migration validation.

Confirm the revised launch date if an approved change notice exists.

# 7. Source limitations

This brief does not contain current readiness percentages, current defect counts, final security approval, a verified cost-of-delay calculation or a confirmed migration-validation owner. Those items must come from later approved evidence or remain Not confirmed.

# 8. Evidence classification challenge

| Statement | Correct treatment |
| --- | --- |
| The pilot launches on 15 September. | Baseline value only; check for an approved later change. |
| The pilot will reduce onboarding to seven days. | Approved target; do not present it as achieved value. |
| The current UAT completion is 92%. | Not available in this source; obtain current readiness evidence. |
| The migration sign-off owner is Elena Novak. | Unsupported; owner remains Not confirmed. |
| The programme is ready to launch. | Not supported by this brief; assess every release gate. |

# 9. Questions before slide creation

Which source contains the latest approved launch date?

Which file is authoritative for current readiness metrics?

Which meeting statements are proposals rather than decisions?

What evidence is still missing, and who must provide it?

Which claims must be labelled target, forecast or Not confirmed?

HANDOFF TO THE NEXT SOURCE Use the Readiness Tracker for current metrics, the Meeting Notes for statements and proposals, and the approved Change Notice for the one named field it overrides.