## Readiness Summary
Project Northstar Readiness Tracker
Cut-off: 26 August 2026 ¦ Synthetic workshop data ¦ Yellow cells are controlled inputs.
Readiness area | Completed | Total | Current % | Required gate | Gate type | Assessment | Evidence / note
UAT | 184 | 200 | 92% | 100% | No Sev-1 defects | Not ready | Four Severity 1 defects remain open
Security | 0 | 1 | 0% | 100% | Approval or restriction | Conditional | Retest booked 10 Sep; external access not approved
Migration | 215 | 250 | 86% | 100% | 250/250 validated | Not ready | 35 supplier records remain
Training | 36 | 50 | 72% | 90% | At least 90% | Not ready | Nine more users needed to reach 45/50
Operations | 0 | 1 | 0% | 100% | Support owner confirmed | Not ready | Support owner is Not confirmed
Financial field | Value |  | Overall release status
Approved budget | 240000 |  | NOT READY - release gates remain open
Spend to date | 218000
Forecast at completion | 252000
Forecast variance | 12000
Forecast variance % | 5% |  | Working recommendation: Conditional Go on 29 Sep 2026 only if every release gate is met. This is not an approved committee decision.

## UAT Defects
UAT Defects
Current UAT evidence. Four open Severity 1 defects prevent release readiness.
Defect ID | Description | Severity | Owner | Status | Target fix | Evidence | Release impact
NS-UAT-041 | Duplicate supplier warning not triggered | Severity 1 | Vendor team | Open | 2026-09-08 | Test run 184 | Blocks release
NS-UAT-052 | Bank verification approval can be bypassed | Severity 1 | Vendor team | Open | 2026-09-08 | Test run 176 | Blocks release
NS-UAT-061 | Compliance evidence missing from export | Severity 1 | Vendor team | Open | 2026-09-08 | Test run 181 | Blocks release
NS-UAT-067 | External supplier invitation expires early | Severity 1 | Vendor team | Open | 2026-09-08 | Test run 183 | Blocks release
NS-UAT-034 | Status email subject inconsistent | Severity 3 | Vendor team | Closed | 2026-08-24 | Retest 179 | No release impact
NS-UAT-038 | Dashboard label truncated | Severity 3 | Vendor team | Closed | 2026-08-25 | Retest 180 | No release impact

## Migration
Supplier Migration Validation
250 pilot suppliers ¦ 215 validated ¦ 35 remain ¦ Final sign-off owner is Not confirmed.
Segment | Supplier count | Validated | Remaining | Completion % | Sign-off owner
Strategic suppliers | 60 | 58 | 2 | 96.67% | Not confirmed
Operational suppliers | 110 | 96 | 14 | 87.27% | Not confirmed
Long-tail suppliers | 80 | 61 | 19 | 76.25% | Not confirmed
Total | 250 | 215 | 35 | 86% | Not confirmed

## Training
Pilot User Training
50 pilot users ¦ 36 trained ¦ 45 required for the 90% release gate.
Business group | Pilot users | Completed | Remaining | Completion % | Status
Procurement | 30 | 24 | 6 | 80% | Below gate
Operations | 20 | 12 | 8 | 60% | Below gate
Total | 50 | 36 | 14 | 72% | Below gate

## Risks and Actions
Risks and Actions
Facts, forecasts and missing ownership are kept separate.
ID | Type | Description | Evidence status | Likelihood | Impact | Mitigation / action | Owner | Due | Decision required
R-01 | Risk | Four Severity 1 defects remain open | Confirmed | High | High | Fix and retest | Daniel Weber | 2026-09-08 | No
R-02 | Risk | External access not approved before security retest | Confirmed | Medium | High | Disable external access until approval | Priya Shah | 2026-09-10 | Yes
R-03 | Risk | 35 supplier records remain unvalidated | Confirmed | Medium | High | Complete validation | Not confirmed |  | Yes
R-04 | Risk | Training is below the 90% release gate | Confirmed | Medium | Medium | Train nine additional users | Sofia Lind |  | No
R-05 | Assumption | Delay costs EUR 35,000 per week | Unsupported vendor statement | Not confirmed | Not confirmed | Obtain Finance calculation | Not confirmed |  | No
A-01 | Action | Confirm first-week support owner | Open |  |  | Nominate and confirm owner | Not confirmed |  | Yes

## Sources
Source Register
Use these IDs in presentation speaker notes and the source-to-slide workbook.
Source ID | Source | Effective date | Authority / use
NS-01 | Project Brief v1.0 | 2026-08-20 | Scope, targets, baseline launch date, budget and release gates
NS-02 | Readiness Tracker | 2026-08-26 | Current readiness metrics, risks and forecast spend
NS-03 | Readiness Review Notes | 2026-08-25 | Statements, proposals, actions and unresolved items
NS-04 | Change Notice CN-NS-014 | 2026-08-27 | Overrides the proposed launch-date field only