LAB 6 APPROVED CREATION SOURCE

Project Northstar - Verified Decision Brief

The controlled Word source for creating the steering committee presentation

| VERSION 1.1 | CUT-OFF 27 August 2026 | PURPOSE Presentation creation |
| --- | --- | --- |

AUTHORITATIVE CREATION SOURCE Create the PowerPoint from this verified brief. Use the other files for audit and traceability, not as permission to add unsupported content.

# 1. Decision required

The Steering Committee must decide whether to approve a conditional pilot launch on 29 September 2026, delay the pilot, or reject the launch. The working recommendation is Conditional Go, but it remains a proposal until the committee approves it.

# 2. Executive readiness summary

| Area | Current evidence | Gate | Assessment |
| --- | --- | --- | --- |
| UAT | 184/200 tests complete (92%); 4 Severity 1 defects open | No open Severity 1 defects | Not ready |
| Security | Retest booked for 10 Sep; external access not approved | Retest passed or restriction approved | Conditional |
| Migration | 215/250 supplier records validated (86%) | 250/250 validated | Not ready |
| Training | 36/50 users trained (72%) | 45/50 users trained (90%) | Not ready |
| Operations | Support owner not confirmed | Owner and triage process confirmed | Not ready |

# 3. Scope and intended value

The pilot scope remains unchanged: supplier intake, evidence collection, compliance workflow, bank-verification hand-off, status tracking and internal notifications for Procurement and Operations. SAP remains the system of record. The cycle-time and follow-up improvements are targets, not realised benefits.

# 4. Financial position

| Approved budget | EUR 240,000 |
| --- | --- |
| Spend to date | EUR 218,000 |
| Forecast at completion | EUR 252,000 |
| Forecast variance | EUR 12,000 over budget (5.0%) |
| Weekly delay cost | Not confirmed - vendor statement only |

# 5. Launch options for the committee

| Option | Conditions / consequence | Evidence status |
| --- | --- | --- |
| A. Conditional Go - 29 Sep | Proceed only if all Severity 1 defects close, security restriction is approved, migration reaches 250/250, training reaches 45/50 and a support owner is confirmed. | Working recommendation; not approved |
| B. Delay | Move the pilot again if any release gate remains unmet. Financial impact cannot be quantified from approved evidence. | Available option |
| C. No Go | Do not launch the pilot and return the programme for replanning. | Available option |

# 6. Risks and unresolved evidence

Four Severity 1 defects are open; the 8 September closure date is a forecast.

External access is not approved before the security retest.

Thirty-five supplier records still require validation.

Nine additional users must complete training to reach the gate.

Migration sign-off owner and support owner are not confirmed.

The EUR 35,000 weekly delay estimate must not appear as a confirmed financial fact.

# 7. Approved single-field change

| Field | Previous value | Current value | Authority |
| --- | --- | --- | --- |
| Proposed pilot launch date | 15 September 2026 | 29 September 2026 | Change Notice CN-NS-014, approved 27 Aug 2026 |

CHANGE BOUNDARY No scope, budget, owner, readiness threshold, risk status or recommendation changed under CN-NS-014.

# 8. Required eight-slide structure

| Slide | Required message |
| --- | --- |
| 1 | Project Northstar - Steering Committee Decision |
| 2 | Executive readiness summary and decision required |
| 3 | Pilot scope and intended business value |
| 4 | Delivery and UAT readiness |
| 5 | Security, migration and operational readiness |
| 6 | Risks, contradictions and missing evidence |
| 7 | Launch options and implications |
| 8 | Required decisions, actions and next steps |

# 9. Presentation controls

Use no more than eight slides.

Separate facts, proposals and missing evidence.

Use Not confirmed when an owner, date or financial value is missing.

Place a source list in the speaker notes for every slide.

Do not create a final committee decision.

Preserve the Northstar corporate template.

# 10. Source register

| ID | Source | Authority / use |
| --- | --- | --- |
| NS-01 | Project Northstar Project Brief v1.0, 20 Aug 2026 | Scope, targets, baseline date, budget and gates |
| NS-02 | Project Northstar Readiness Tracker, cut-off 26 Aug 2026 | Current readiness metrics and forecast spend |
| NS-03 | Project Northstar Readiness Review Notes, 25 Aug 2026 | Statements, proposals and unresolved items |
| NS-04 | Change Notice CN-NS-014, 27 Aug 2026 | Overrides the launch-date field only |

# 11. Approved PowerPoint generation instruction

CREATION PROMPT Create an eight-slide steering committee presentation from this verified brief. Use the open Northstar corporate template. Preserve its theme and layouts. Follow the required slide structure. Separate confirmed facts, proposals and missing evidence. Add concise speaker notes with a [Sources] block on every slide. Do not add facts from general knowledge or make the final committee decision.

# 12. Mandatory human checks

Compare every visible number and date with the Readiness Tracker and Change Notice.

Remove or label any unsupported financial statement.

Confirm that Conditional Go remains a proposal.

Confirm that the 29 September date appears only where relevant.

Review speaker notes and run PowerPoint Accessibility Checker.