## Slide 1
NORTHSTAR GROUP
Project Northstar
Steering Committee decision | Proposed pilot: 29 September 2026
Supplier Onboarding Platform
Synthetic workshop case | Trainer answer deck
Notes: Open with the decision date and clarify that this is a proposed conditional launch, not an approved outcome.
Ask the committee to focus on the five release gates.
[Sources]
- NS-04 - Change Notice CN-NS-014
- Verified Decision Brief v1.1

## Slide 2
DECISION REQUIRED
Four release gates remain open
WORKING RECOMMENDATION - NOT APPROVED
Approve a Conditional Go for 29 September only if every release gate is met.
NOT READY
Current release status
4 of 5 areas are not ready
UAT: four Severity 1 defects remain open
Security: external access is not approved
Migration, training and support ownership remain below gate
Committee decision: Conditional Go, Delay or No Go?
PROJECT NORTHSTAR | STEERING COMMITTEE
2
Notes: Lead with status, not activity.
Conditional Go is the programme team's working recommendation only.
Do not present the EUR 35,000 weekly delay statement as a financial fact.
[Sources]
- NS-02 - Readiness Tracker
- NS-03 - Readiness Review Notes
- NS-04 - Change Notice CN-NS-014

## Slide 3
PILOT SCOPE
The scope is unchanged; benefits remain targets
IN SCOPE
Supplier intake and document collection
Compliance workflow and audit evidence
Bank-verification hand-off
Status tracking and internal notifications
TARGET VALUE
12 -> 7 days
Onboarding cycle target
Within three months of launch
-30%
Manual follow-up target
Within three months of launch
These are approved targets - not benefits already realised.
PROJECT NORTHSTAR | STEERING COMMITTEE
3
Notes: Keep the scope and target value separate.
SAP remains the system of record.
Do not describe the target measures as achieved outcomes.
[Sources]
- NS-01 - Project Brief v1.0

## Slide 4
DELIVERY READINESS
Four Severity 1 defects block launch readiness
Chart: 
| Tests complete | Tests remaining
Count | 184 | 16
92%
UAT complete
184 of 200 planned tests
4 OPEN
Severity 1 defects
Release gate requires zero
Vendor forecasts fixes by 8 September; closure is not confirmed.
PROJECT NORTHSTAR | STEERING COMMITTEE
4
Notes: Explain why percentage alone is insufficient.
The four Severity 1 defects block readiness.
The 8 September date is a vendor forecast and must be labelled accordingly.
[Sources]
- NS-02 - Readiness Tracker, Readiness Summary
- NS-02 - UAT Defects
- NS-03 - Readiness Review Notes

## Slide 5
OPERATIONAL READINESS
Security, migration, training and ownership remain conditional
Conditional
SECURITY
Retest 10 Sep; external access not approved
86%
MIGRATION
215/250 validated; sign-off owner not confirmed
72%
TRAINING
36/50 complete; gate requires 45/50
Not confirmed
SUPPORT
Owner and first-week triage must be confirmed
All four conditions require human confirmation before launch.
PROJECT NORTHSTAR | STEERING COMMITTEE
5
Notes: State the numeric gates and the ownership gaps.
Do not infer a migration or support owner.
External access can remain disabled only under an approved restriction.
[Sources]
- NS-01 - Project Brief v1.0
- NS-02 - Readiness Tracker
- NS-03 - Readiness Review Notes

## Slide 6
EVIDENCE RISKS
Three claims still need correction or confirmation
UNSUPPORTED
EUR 35,000 weekly delay cost
Vendor statement only; no Finance calculation supplied
PROPOSAL
Conditional Go
Working recommendation; Steering Committee has not approved it
MISSING
Migration and support owners
Both remain Not confirmed
PROJECT NORTHSTAR | STEERING COMMITTEE
6
Notes: This slide makes uncertainty visible rather than resolving it through design.
Ask Finance to validate the delay-cost calculation.
Keep missing owners explicit.
[Sources]
- NS-03 - Readiness Review Notes
- Verified Decision Brief v1.1

## Slide 7
LAUNCH OPTIONS
Conditional Go remains viable only if every gate is met
A
Conditional Go
29 Sep
Proceed only when all five release conditions are satisfied.
Working recommendation - not approved
B
Delay
New date TBD
Move the pilot if any release gate remains open.
Available committee option
C
No Go
Replan
Stop the pilot and return the programme for replanning.
Available committee option
PROJECT NORTHSTAR | STEERING COMMITTEE
7
Notes: Compare all three options using the same decision criteria.
Option A uses the approved 29 September date.
Do not quantify the cost of Option B without Finance evidence.
[Sources]
- NS-04 - Change Notice CN-NS-014
- Verified Decision Brief v1.1

## Slide 8
DECISIONS REQUIRED TODAY
Make the launch decision with explicit conditions
01
Approve Conditional Go for 29 September, Delay or No Go
02
Approve the temporary external-access restriction
03
Confirm migration sign-off and support owners
04
Require evidence that all release gates are met before launch
Copilot prepared the evidence. The Steering Committee owns the decision.
NORTHSTAR GROUP | DECISION
Notes: Read the four required decisions aloud.
Ask the committee to correct any evidence before deciding.
Record the final decision separately from this draft deck.
[Sources]
- Verified Decision Brief v1.1
- NS-01 - Project Brief v1.0
- NS-02 - Readiness Tracker
- NS-03 - Readiness Review Notes
- NS-04 - Change Notice CN-NS-014