## Read Me
Lab 8 - Project Aurora Control Register
Synthetic source pack for the Project Delivery Control agent. The deliberate gaps and conflicts are part of the exercise.
Step | Instruction | Direct-update prompt
1 | Save this workbook in the approved SharePoint workshop folder. | In this workbook, add the approved field-level changes to the Controlled Changes table. Use the Project ID and Field Name as the key. Preserve the current value exactly, add only the approved proposed value, and include the evidence reference. Do not modify Project Register. Stop and ask me if any required value is missing.
2 | Use Project Register as the authoritative current record.
3 | Use Weekly Update Evidence as a later, lower-authority source.
4 | Ask the agent for field-level deltas; do not accept broad record rewrites.
5 | For approved changes, open this file in Excel and ask Copilot in Excel to write directly to Controlled Changes.
6 | Do not manually copy agent output into the workbook.
7 | Ask Copilot to change only the named field and keep every other field unchanged.

## Project Register
Project ID | Project Name | Department | PM Role | Sponsor Role | Stage | RAG Status | Approved Budget | Forecast Cost | Budget Variance | Planned Go-Live | Forecast Go-Live | Schedule Variance Days | Open High Risks | Open Critical Issues | Last Update Date | Decision Required | Decision Owner | Evidence Status | Source Version | Data Classification
IT-003 | Data Retention Compliance | Security | PM-03 | SP-03 | Build | Amber | 140000 | 150000 | 10000 | 2026-11-01 | 2026-11-12 | 11 | 2 | 1 | 2026-08-24 | Yes | SP-03 | Partial | Register v6 | Synthetic training data
IT-005 | Finance Reporting Automation | Finance | PM-05 | SP-04 | UAT | Amber | 225000 | 239000 | 14000 | 2026-09-30 | 2026-10-10 | 10 | 2 | 0 | 2026-08-23 | Yes | SP-04 | Confirmed | Register v6 | Synthetic training data
IT-006 | Legacy VPN Retirement | Security | PM-03 | SP-03 | Build | Red | 160000 | 198000 | 38000 | 2026-09-15 | 2026-11-01 | 47 | 5 | 2 | 2026-08-26 | No |  | Partial | Register v6 | Synthetic training data
IT-009 | Enterprise Search Upgrade | Digital Workplace |  | SP-02 | Planning | Amber | 275000 | 275000 | 0 | 2027-01-15 | 2027-01-29 | 14 | 2 | 0 | 2026-08-21 | Yes | SP-02 | Partial | Register v6 | Synthetic training data
IT-012 | Security Operations Analytics | Security | PM-03 | SP-03 | Planning | Amber | 360000 | 382000 | 22000 | 2027-02-15 | 2027-02-28 | 13 | 3 | 0 | 2026-08-25 | Yes |  | Partial | Register v6 | Synthetic training data
IT-014 | Warehouse Mobility | Operations | PM-11 | SP-02 | UAT | Red | 500000 | 548000 | 48000 | 2026-09-10 | 2026-10-20 | 40 | 6 | 3 | 2026-08-27 | Yes | SP-02 | Confirmed | Register v6 | Synthetic training data
IT-015 | ESG Data Collection | Sustainability | PM-05 | SP-06 | Build | Green | 190000 | 194000 | 4000 | 2026-10-01 | 2026-11-15 | 45 | 2 | 0 | 2026-08-24 | No |  | Partial | Register v6 | Synthetic training data
IT-017 | IT Service Catalogue | Service Management | PM-06 | SP-02 | UAT | Amber | 175000 | 181000 | 6000 | 2026-09-25 | 2026-10-02 | 7 | 2 | 1 | 2026-08-26 | Yes | SP-02 | Confirmed | Register v6 | Synthetic training data
IT-018 | Archive Platform Migration | Infrastructure | PM-04 | SP-01 | Planning | Amber | 260000 | -5000 | -265000 | 2027-01-30 | 2027-02-15 | 16 | 2 | 0 | 2026-08-18 | Yes | SP-01 | Missing | Register v6 | Synthetic training data
IT-020 | Privileged Access Management | Security | PM-03 | SP-03 | UAT | Red | 450000 | 489000 | 39000 | 2026-09-05 | 2026-10-15 | 40 | 7 | 2 | 2026-08-27 | Yes | SP-03 | Confirmed | Register v6 | Synthetic training data
IT-021 | Field Service Scheduling | Operations | PM-11 | SP-02 | Build | Amber | 205000 | 218000 | 13000 | 2026-10-20 | 2026-11-05 | 16 | 3 | 0 | 2026-07-25 | Yes | SP-02 | Partial | Register v6 | Synthetic training data
IT-030 | Records Classification | Legal | PM-10 | SP-07 | Discovery |  | 80000 | 82000 | 2000 | 2027-05-01 | 2027-05-01 | 0 | 1 | 0 | 2026-08-10 | No |  | Missing | Register v6 | Synthetic training data

## Weekly Update Evidence
Weekly Update Evidence
Lower-authority source. Copilot must preserve suggestions and conflicts instead of silently changing the register.
Evidence ID | Project ID | Date | Update statement | Evidence type | Explicitly confirmed? | Expected interpretation | Data Classification
WU-001 | IT-017 | 2026-08-28 | Steering chair confirmed the project is now Red. All other register fields remain unchanged. | Signed weekly update | Yes | Propose only RAG Status: Amber → Red | Synthetic training data
WU-002 | IT-005 | 2026-08-28 | PM confirmed forecast go-live is 17 October 2026. No other baseline change was approved. | Signed weekly update | Yes | Propose only Forecast Go-Live: 10 Oct → 17 Oct 2026 | Synthetic training data
WU-003 | IT-014 | 2026-08-28 | Critical issue count increased from 3 to 4. Existing owners and dates are unchanged. | Signed weekly update | Yes | Propose only Open Critical Issues: 3 → 4 | Synthetic training data
WU-004 | IT-012 | 2026-08-28 | SP-03 accepted ownership of the decision required. No decision has yet been made. | Signed weekly update | Yes | Propose only Decision Owner: blank → SP-03 | Synthetic training data
WU-005 | IT-018 | 2026-08-28 | Working estimate may be €285,000, subject to finance validation. | Draft chat note | No | Conflict with invalid register value; label Not confirmed and request validation | Synthetic training data
WU-006 | IT-021 | 2026-08-28 | The team thinks the project should probably be Green after next sprint. | Meeting note | No | Suggestion only; do not propose RAG change | Synthetic training data
WU-007 | IT-015 | 2026-08-28 | The team remains confident despite the 45-day forecast delay. | Meeting note | No | Surface inconsistency; do not infer a new RAG | Synthetic training data

## Controlled Changes
Controlled Changes
Use Copilot in Excel to write approved changes directly to this table. Do not manually copy text from Copilot Chat.
Change ID | Project ID | Field Name | Current Value | Proposed Value | Evidence ID | Evidence Quote | Validation Status | Approved? | Applied? | Reviewer | Audit Note