Project Nova - Weekly Status Report

Approved baseline for the weekly review

| Document ID | PN-SR-004 |
| --- | --- |
| Version | 4.0 |
| Status | Approved |
| Approved by | Elena Rossi, Programme Director |
| Approved date | 2026-08-27 |

# Executive position

Overall delivery status is Amber. The programme remains within the approved budget, but UAT cannot begin until the named security and technical conditions in Decision D-031 are satisfied.

| Measure | Approved value | Interpretation |
| --- | --- | --- |
| Overall status | Amber | Management attention required; no stop decision recorded. |
| Approved budget | EUR 260,000 | Current approved programme ceiling. |
| Actual spend | EUR 182,000 | 70.0% of approved budget. |
| Open defects | 7 total | Two are High severity; five are Medium or Low. |
| Security test | 76 of 80 checks passed | Four checks remain open; sign-off not granted. |
| Target UAT date | 2026-09-15 | Planning target only; conditional and not yet approved. |
| Approved UAT scope | Maximum 40 users | Per Decision D-031; expansion requires a new decision. |

# Required decisions

Security Owner must confirm whether the four remaining checks are acceptable for UAT.

Programme Director must confirm whether all D-031 entry conditions are met before announcing a start date.